## Sheet1
ID | Activities | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
1.0 | Planning
Task Allocation through meeting | bar: 15
2.0 | Interview Process | bar: 15 to 22
Organization model discussion and selection | bar: 15 to 16
Approaching the organizations | bar: 16 to 19
Interview Session (trial and error included) | bar: 19 to 22
3.0 | Requirements after interview | bar: 15 to 22
Introduction | bar: 21 to 23
Business Rules | bar: 21 to 23
System Objectives and Scope | bar: 22 to 25
User requirements | bar: 22 to 25
Entities and attributes | bar: 22 to 25
5.0 | ERD Segments | bar: 23 to 25
6.0 | Normalization | bar: 23 to 25
7.0 | Powerpoint Slides | bar: 15 to 29
WEEK 8 is 2nd dec